## Project - Project Plan - START
Title | URL | Assignees | Status | Start Date | End Date
Updating the requirements | https://github.com/bounswe/bounswe2023group9/issues/260 | uyduranomer, Zulalm | ✅ Done | 2023-10-09 | 2023-10-17
Review of the RAM table | https://github.com/bounswe/bounswe2023group9/issues/262 | hakanaktas0 | ✅ Done | 2023-10-10 | 2023-10-13
Updating the UML diagrams according to the updates in the requirements | https://github.com/bounswe/bounswe2023group9/issues/261 | Brunettow, laylaylo, Zulalm | 🔖 Ready-to-start | 2023-10-10 | 2023-11-08
Designing file structure outlines for front-end | https://github.com/bounswe/bounswe2023group9/issues/254 | omerfaunal | ✅ Done | 2023-10-10 | 2023-10-11
Designing file structure outlines for back-end | https://github.com/bounswe/bounswe2023group9/issues/270 | ArslanArdavic, Bera0422, hakanaktas0, uyduranomer | ✅ Done | 2023-10-10 | 2023-10-11
Database should be initialized | https://github.com/bounswe/bounswe2023group9/issues/271 | ArslanArdavic, Bera0422, gebenalimert, hakanaktas0, oguzpancuk, uyduranomer | ✅ Done | 2023-10-10 | 2023-10-11
New Labels should be created | https://github.com/bounswe/bounswe2023group9/issues/272 | hakanaktas0 | ✅ Done | 2023-10-11 | 2023-10-25
Review of the Project Plan | https://github.com/bounswe/bounswe2023group9/issues/252 | hakanaktas0, Zulalm | ✅ Done | 2023-10-11 | 2023-10-14
Login Page | https://github.com/bounswe/bounswe2023group9/issues/267 | mehmetSuzer | ✅ Done | 2023-10-12 | 2023-10-19
Signup Page | https://github.com/bounswe/bounswe2023group9/issues/266 | Brunettow, mehmetSuzer, omerfaunal, Zulalm | ✅ Done | 2023-10-12 | 2023-10-19
Defining authentication mechanisms | https://github.com/bounswe/bounswe2023group9/issues/265 | hakanaktas0, uyduranomer | ✅ Done | 2023-10-12 | 2023-10-19
Designing file structure outlines for back-end | https://github.com/bounswe/bounswe2023group9/issues/263 |  | ✅ Done | 2023-10-12 | 2023-10-14
Deciding and setting up development, testing environment | https://github.com/bounswe/bounswe2023group9/issues/264 |  | ✅ Done | 2023-10-12 | 2023-10-15
Automated Testing and Deployment for Backend | https://github.com/bounswe/bounswe2023group9/issues/278 | hakanaktas0 | 📋 Backlog | 2023-10-12 | 2023-11-09
Creating User Models | https://github.com/bounswe/bounswe2023group9/issues/255 | Bera0422, uyduranomer | ✅ Done | 2023-10-13 | 2023-10-14
Frontend Auth Provider | https://github.com/bounswe/bounswe2023group9/issues/274 | defabdullah, omerfaunal | ✅ Done | 2023-10-13 | 2023-10-19
Get authenticated user GET API | https://github.com/bounswe/bounswe2023group9/issues/275 | uyduranomer | ✅ Done | 2023-10-13 | 2023-10-15
Unit Tests for the API methods | https://github.com/bounswe/bounswe2023group9/issues/277 | Bera0422 | ✅ Done | 2023-10-13 | 2023-10-15
CORS policy fix for Backend | https://github.com/bounswe/bounswe2023group9/issues/279 | hakanaktas0 | ✅ Done | 2023-10-14 | 2023-10-15
Signup Page POST API | https://github.com/bounswe/bounswe2023group9/issues/256 | uyduranomer | ✅ Done | 2023-10-15 | 2023-10-16
Login Page POST API | https://github.com/bounswe/bounswe2023group9/issues/257 | uyduranomer | ✅ Done | 2023-10-15 | 2023-10-16
Contributor Class/Model Implementation | https://github.com/bounswe/bounswe2023group9/issues/293 | ArslanArdavic | ✅ Done | 2023-10-17 | 2023-10-23
Reviewer Class/Model Implementation | https://github.com/bounswe/bounswe2023group9/issues/292 | ArslanArdavic | ✅ Done | 2023-10-17 | 2023-10-23
Weekly Progress Report #3 | https://github.com/bounswe/bounswe2023group9/issues/284 |  | ✅ Done | 2023-10-17 | 2023-10-18
Question Class/Model Implementation | https://github.com/bounswe/bounswe2023group9/issues/298 | uyduranomer | ✅ Done | 2023-10-17 | 2023-10-23
Proof Class/Model Implementation | https://github.com/bounswe/bounswe2023group9/issues/297 | Bera0422 | ✅ Done | 2023-10-17 | 2023-10-19
Theorem Class/Model Implementation | https://github.com/bounswe/bounswe2023group9/issues/296 | Bera0422 | ✅ Done | 2023-10-17 | 2023-10-19
Semantic Tag Class/Model Implementation | https://github.com/bounswe/bounswe2023group9/issues/299 | uyduranomer | ✅ Done | 2023-10-17 | 2023-10-23
Home Page | https://github.com/bounswe/bounswe2023group9/issues/289 | defabdullah, mehmetSuzer, omerfaunal | ✅ Done | 2023-10-17 | 2023-10-23
Generic Parent Page | https://github.com/bounswe/bounswe2023group9/issues/290 | omerfaunal | ✅ Done | 2023-10-17 | 2023-10-23
Profile Page GET API | https://github.com/bounswe/bounswe2023group9/issues/285 | hakanaktas0 | ✅ Done | 2023-10-17 | 2023-10-23
Home Page GET API | https://github.com/bounswe/bounswe2023group9/issues/286 | hakanaktas0 | ✅ Done | 2023-10-17 | 2023-10-23
Admin Class/Model Implementation | https://github.com/bounswe/bounswe2023group9/issues/291 | ArslanArdavic | ✅ Done | 2023-10-17 | 2023-10-23
Profile Page | https://github.com/bounswe/bounswe2023group9/issues/288 | Brunettow, laylaylo, Zulalm | ✅ Done | 2023-10-17 | 2023-10-30
Change page structures with new generic page design | https://github.com/bounswe/bounswe2023group9/issues/315 | omerfaunal | ✅ Done | 2023-10-18 | 2023-10-29
Transfer Project Plan to Github Project Road Map Page | https://github.com/bounswe/bounswe2023group9/issues/283 | hakanaktas0 | ✅ Done | 2023-10-19 | 2023-10-22
Node Class/Model Implementation | https://github.com/bounswe/bounswe2023group9/issues/294 | Bera0422 | ✅ Done | 2023-10-19 | 2023-10-21
FrontEnd Models | https://github.com/bounswe/bounswe2023group9/issues/311 | defabdullah, omerfaunal | ✅ Done | 2023-10-19 | 2023-10-26
Revise Login and Sign Up Page | https://github.com/bounswe/bounswe2023group9/issues/314 | omerfaunal | ✅ Done | 2023-10-19 | 2023-10-31
Bug: Backend should return different error messages | https://github.com/bounswe/bounswe2023group9/issues/287 | ArslanArdavic, hakanaktas0, uyduranomer | ✅ Done | 2023-10-20 | 2023-10-28
Node view Page | https://github.com/bounswe/bounswe2023group9/issues/321 | Zulalm | ✅ Done | 2023-10-24 | 2023-11-07
Profile Settings Page PUT API | https://github.com/bounswe/bounswe2023group9/issues/323 | uyduranomer | ✅ Done | 2023-10-24 | 2023-10-30
Preparation for Deployment and Revision for Customer Milestone 1 | https://github.com/bounswe/bounswe2023group9/issues/325 |  | 🏗 In progress | 2023-10-24 | 2023-10-30
Weekly progress report #4 | https://github.com/bounswe/bounswe2023group9/issues/333 |  | ✅ Done | 2023-10-24 | 2023-10-24
Node View Page GET API | https://github.com/bounswe/bounswe2023group9/issues/324 | Bera0422 | ✅ Done | 2023-10-24 | 2023-10-30
Enhancement for Profile Page | https://github.com/bounswe/bounswe2023group9/issues/332 | laylaylo, Zulalm | ✅ Done | 2023-10-24 | 2023-10-31
Settings page | https://github.com/bounswe/bounswe2023group9/issues/322 |  | ✅ Done | 2023-10-24 | 2023-10-30
Enhancement for Home Page | https://github.com/bounswe/bounswe2023group9/issues/328 | mehmetSuzer, omerfaunal | ✅ Done | 2023-10-25 | 2023-10-31
Profile Page GET API Update | https://github.com/bounswe/bounswe2023group9/issues/337 | hakanaktas0 | ✅ Done | 2023-10-25 | 2023-10-28
Theorem Model GET API Implementation | https://github.com/bounswe/bounswe2023group9/issues/327 | ArslanArdavic | ✅ Done | 2023-10-25 | 2023-10-29
Proof Model GET API Implementation | https://github.com/bounswe/bounswe2023group9/issues/326 | ArslanArdavic | ✅ Done | 2023-10-25 | 2023-10-30
Add Search Functionality to Home Page - FE | https://github.com/bounswe/bounswe2023group9/issues/331 | defabdullah, omerfaunal | ✅ Done | 2023-10-25 | 2023-10-31
Dockerfile should be created | https://github.com/bounswe/bounswe2023group9/issues/339 | hakanaktas0 | ✅ Done | 2023-10-28 | 2023-10-30
Password Change PUT api will be implemented | https://github.com/bounswe/bounswe2023group9/issues/330 | uyduranomer | ✅ Done | 2023-10-29 | 2023-10-31
FE - Signup Login Flow Bug Fix | https://github.com/bounswe/bounswe2023group9/issues/347 | omerfaunal | ✅ Done | 2023-10-29 | 2023-10-30
Workspace Model/Class Implementation | https://github.com/bounswe/bounswe2023group9/issues/356 | gebenalimert | 🏗 In progress | 2023-10-30 | 2023-11-05
Contributor GET API | https://github.com/bounswe/bounswe2023group9/issues/361 | hakanaktas0 | ✅ Done | 2023-10-30 | 2023-10-30
Workspace Page |  | Brunettow, laylaylo, mehmetSuzer, omerfaunal, Zulalm | INACTIVE | 2023-10-31 | 2023-11-20
Entry Class Implementation |  | gebenalimert | INACTIVE | 2023-10-31 | 2023-11-06
Request Class Implemenation |  | Bera0422 | INACTIVE | 2023-10-31 | 2023-11-06
ReviewRequest Class Implementation |  | Bera0422 | INACTIVE | 2023-10-31 | 2023-11-06
CollaborationRequest Class Implementation | https://github.com/bounswe/bounswe2023group9/issues/305 | Bera0422 | INACTIVE | 2023-10-31 | 2023-11-06
Review Class Implementation |  | hakanaktas0 | INACTIVE | 2023-10-31 | 2023-11-06
Front End Dockerfile | https://github.com/bounswe/bounswe2023group9/issues/368 | hakanaktas0 | ✅ Done | 2023-10-31 | 2023-11-01
Customer Milestone 1 Report | https://github.com/bounswe/bounswe2023group9/issues/374 |  | 🏗 In progress | 2023-11-01 | 2023-11-03
Search Enhancement | https://github.com/bounswe/bounswe2023group9/issues/344 | hakanaktas0 | 📋 Backlog | 2023-11-02 | 2023-11-16
Contributor Class/Model Enhancement | https://github.com/bounswe/bounswe2023group9/issues/304 | ArslanArdavic | 📋 Backlog | 2023-11-02 | 2023-11-12
Reviewer Class/Model Enhancement | https://github.com/bounswe/bounswe2023group9/issues/306 | ArslanArdavic | 📋 Backlog | 2023-11-02 | 2023-11-11
Admin Class/Model Enhancement | https://github.com/bounswe/bounswe2023group9/issues/307 | ArslanArdavic | 📋 Backlog | 2023-11-02 | 2023-11-11
Admin panel Page |  | Brunettow, defabdullah, laylaylo, mehmetSuzer, omerfaunal, Zulalm | INACTIVE | 2023-11-04 | 2023-11-08
Admin panel GET API |  | ArslanArdavic, oguzpancuk | INACTIVE | 2023-11-04 | 2023-11-08
Admin panel POST API |  | ArslanArdavic | INACTIVE | 2023-11-04 | 2023-11-08
Reviewer randomizer |  | hakanaktas0 | INACTIVE | 2023-11-07 | 2023-11-13
Annotation Class Implementation |  | uyduranomer | INACTIVE | 2023-11-07 | 2023-11-13
Weekly progress report #6 |  |  | INACTIVE | 2023-11-07 | 2023-11-07
Workspace page GET API |  | ArslanArdavic, gebenalimert | INACTIVE | 2023-11-14 | 2023-11-20
Workspace page POST API |  | uyduranomer | INACTIVE | 2023-11-14 | 2023-11-20
Weekly progress report #7 |  |  | INACTIVE | 2023-11-14 | 2023-11-14
Graph Page |  | Brunettow, defabdullah, laylaylo, mehmetSuzer, omerfaunal, Zulalm | INACTIVE | 2023-11-21 | 2023-12-11
Graph page GET API |  | hakanaktas0 | INACTIVE | 2023-11-21 | 2023-12-04
Graph page POST API |  | uyduranomer | INACTIVE | 2023-11-21 | 2023-12-04
Notification Class Implementation |  | ArslanArdavic | INACTIVE | 2023-11-21 | 2023-11-27
Deployment and review for Customer Milestone 2 |  |  | INACTIVE | 2023-11-21 | 2023-11-27
Weekly progress report #8 |  |  | INACTIVE | 2023-11-21 | 2023-11-21
Weekly progress report #9 |  |  | INACTIVE | 2023-11-28 | 2023-11-28
Role-related access control |  | uyduranomer | INACTIVE | 2023-12-05 | 2023-12-11
Review and Fine Tune |  |  | INACTIVE | 2023-12-05 | 2023-12-25
Weekly progress report #10 |  |  | INACTIVE | 2023-12-05 | 2023-12-05
Writing Privacy Policy |  | ArslanArdavic, Bera0422, gebenalimert, hakanaktas0, oguzpancuk, uyduranomer | INACTIVE | 2023-12-12 | 2023-12-18
Weekly progress report #11 |  |  | INACTIVE | 2023-12-12 | 2023-12-12
Final Milestone Deployment and Review |  |  | INACTIVE | 2023-12-19 | 2023-12-25
Weekly progress report |  |  | INACTIVE | 2023-12-19 | 2023-12-19